## Backlog
ID | Importance | Title | User Story | Acceptance Criteria | Estimate
Note on A1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I changed “Id.” to “ID.” Confirm.

## Backlog filled
Id. | Importance | Title | User Story | Acceptance Criteria | Status
2 | 10 | Login to my account | As a User, I want to Login to my account using my username, cardID and password so that I can perform the transaction | 1. System must validate my username and password 2. In case the User enters a wrong password and or CardID, the system should prompt the user to enter the correct password, 3. If the password is correct then the user should successfully entered the system | Done
1 | 20 | Checking my account transaction history | As a User, I want to check the balance of my bank account so that I can perform transaction | 1. User need to be logged in before checking the transaction history which must include the following fields Card No.., name, Balance and current cash withdraw limit | Done
3 | 30 | Deposit money to account | As a User I want to deposit money in my bank account through ATM so that I may save time and perform transactions later | 1. User need to be logged in before depositing cash. 2. System should verify the amount of money deposited by checking with user | Done
4 | 40 | Withdraw money from my account | As a User, I want to withdraw money from my bank account through ATM so that I may save my time | 1. User need to be logged in before withdrawing money. 2. System checks if the request amount exceeds the balance. 3. If so the system displays the balance and ask the user to enter a new amount | Done
5 | 50 | Transfer money between account in the system | As a User I want to transfer money from my account to another bank account through ATM so that I may save time | 1.User need to be logged in before transfering money. 2. System should check the recievers account number and validate the last name of the account owner prior to performing transaction. 3. If ok system should update both account concurrently. | Done
6 | 60 | Changing password | As a User, I should be able to changed my password | 1. User need to be logged in before changing their password. 2.System asks User to enter their current password . 3. if correct then system ask the user to enter a new password | Done
7 | 70 | Logged out seeseion | As a User, I want to Logout from my bank account through ATM so that I may end up my ATM session | 1. User is logged off from the account. 2. System dispay a message and return back to the home page. | Done